## Slide 1
Annual Report – Videoconference
23 Oct 2014

## Slide 2: Agenda
10:00 Project overview /goals Reidun Gangdal
10:10 Key achievements / problems of Year 1 Hai Ying Liu
Nuria Castell
Mirjam Fredriksen
Arne Berre
Josef Noll
Reidun Gangdal
10:30 Outreach to target groups / feedback Erol Cagatay
10:50 Planned activities for Year 2 Nuria Castell
Arne Berre
Josef Noll
Erol Cagatay
11:00 Comments on Interim Report / Deliverables Commission
11:30 Conclusions / Actions All

## Slide 3: Citi-Sense-MOB vision
The quality of life in cities is affected by the negative impacts of increasing traffic levels.
People who live, work and play near major roadways may experience health effects from traffic pollution.
New research conducted in 10 European cities has estimated that 14% of chronic childhood asthma is due to exposure to traffic pollution near busy roads.
Important problems:
Large-scale air pollution measurement in urban environments
More data, more noise but also more redundancy
Key challenges in public participation
Key challenges in information systems
Merge different types of information: from global (satellites) to street-level (sensors)
Opportunities and challenges:
Few monitoring stations
No real-time data near-road
Air pollution model development
Policy making and urban planning
Transportation and air quality policies

## Slide 4
The Citi-Sense-MOB consortium will..
…develop, test and demonstrate new mobile services that exhibit the potential for mobile technologies…
…to provide citizens and authorities with information related to environmental quality (air pollution/climate gas emissions) to support green growth in the Oslo area
Sep 1st 2013 – Aug 31st 2015
Budget: 715,000 €
“Large-scale demonstrators in support of GMES and GNSS based services”
Develop key end user mobile device applications
Develop and demonstrate innovative mobile services based on GMES and GNSS systems services from GEOSS

## Slide 5
Beneficiaries | Major role
Kjeller Innovasjon | 1 Coordinator
NILU | 2 Air quality and tech. project lead
SINTEF | 3 IT infrastructure
UNIK | 4 Technical development
MOVATION | 5 App development
Partners
Suppliers
Ingenieros Asesores S.A.
ADN Context-Aware Mobile Solutions, S.L.
Target groups
Oslo Kommune RUTER Nobina

## Slide 6: Project organization
WP 1: NILU
WP 2: NILU
WP 3: NILU
WP 4: SINTEF
WP 5: Kjeller Innovasjon

## Slide 7: Key Achievements / Issues - WP1
Design of services
Overview of the system design, requirements, specifications and architecture for the COT
Exploring the COT (Citizen Observatory Toolbox):
  The concept for COT
  A set of COT (e.g., data, web apps, mobile apps, maps, services, methodologies, etc.)
  Service design concept (i.e., use of ATONE –method for service design)
  The COT target groups

## Slide 8: Key Achievements / Issues - WP1
Key achievements
Submitted D1.1
Article on ‘Mobile technologies and services for environmental monitoring: The Citi-Sense-MOB approach’
Presentation on ‘Mobile technologies and services for supporting green mobility in Oslo: the Citi-Sense-MOB approach’ was given at Renewable Energy Research Conference (RERC), Oslo, 16-18 June, 2014

## Slide 9: Key Achievements / Issues - WP2
Implementation and evaluation of low-cost sensors for monitoring the environment on mobile platforms.
Data Fusion
Dunavnet EB700 (On bikes)
Environmental Parameters
CO, CO2, NO, NO2, O3, SO2, Pre, T, RH
Power consumption
External supply of 8-28V DC
Communication
GPRS
UrVamm (On buses)
Environmental Parameters
CO, NO2, T and RH
Power consumption
External supply of 12-24V DC
Communication
GPRS
Ateknea PSP (personal)
Environmental Parameters
CO, NO2, O3, T and RH
Power consumption
Battery 3.7V LiPo 1300mAh
Communication
Bluetooth

## Slide 10: Key Achievements / Issues - WP2
Key Achievements
D2.1 and D2.2 have been submitted
First road trials performed: bus, bike and personal
Implementation and laboratory calibration
Peer reviewed paper and talks in conferences
Issues
Pre-commercial units. 4 months delay in installation
Data communication problems with the bus installation

## Slide 11: Key Achievements / Issues - WP3

## Slide 12: Key Achievements / Issues - WP3
Key achievements
  Issues
Due to sensor and platform delays, D3.2 and D.3.3 combined and finished M13 (M4-6)

## Slide 13: Key Achievements / Issues – WP4

## Slide 14: Key Achievements / Issues – WP4

## Slide 15: Key Achievements / Issues - WP4
(Josef Noll)

## Slide 16: Outreach to target groups
Bus ?
Bicycle
On person
More personal due to
carrier involvement
Local Government
Oslo Kommune
Others
Interest
Groups
Data User
Data Miners
App developers
End User
Kindergartens
Cyclists
Respiratory d.

## Slide 17: Outreach to target groups
Activities
Meetings with focus groups
Oslo Kommune
Ruter/Nobina
Health consultants
Parking Wardens
Presentations
Renewable
OIW
Enviro
Media
NRK
Gemini magazine
OIW
Internet/Social media
Homepage
Facebook
Linkedin
Twitter

## Slide 18: Planned activities for Year 2
INCREASING APP USE
NOV 2014
DEC 2014
JAN 2015
FEB 2015
MAR 2015
APR 2015
MAY 2015
JUL 2015
AUG 2015
Traffic wardens and cyclists
Possible bus installation
Workshop with Kindergartens
Workshop with data miners/app developers
Test of new PM sensor
New app version distributed
New app version distributed
VGI work starts
Workshop with users
D 2.3
D 4.5
D 4.7
D 5.4
Distribution of more sensors
Preparation for traffic wardens

## Slide 19: Planned activities for Year 2
INCREASING APP USE
NOV 2014
DEC 2014
JAN 2015
FEB 2015
MAR 2015
APR 2015
MAY 2015
JUL 2015
AUG 2015
SEP 2015
OCT 2015
NOV 2015
DEC 2015
Traffic wardens and cyclists
Possible bus installation
Workshop with Kindergartens
Workshop with data miners/app developers
Test of new PM sensor
New app version distributed
New app version distributed
VGI work starts
Workshop with users
D 2.3
D 4.5
D 4.7
D 5.4
Distribution of more sensors
Preparation for traffic wardens

## Slide 20: Planned activities for Year 2
(Nuria Castell)

## Slide 21: Planned activities for Year 2
More sensors & data & VGI
App release
Social Media Integration & App feedback
Update of the App
Toolbox def. for developers and data users
Revisit target groups
Mapping target groups
Roadmap of novel services
Dissemination
Exploitation

## Slide 22: Planned activities for Year 2
Discussions with other cities
Planned activities with Oslo Kommune
Reaching out to cyclists
Workshops with developers
Workshops/seminars for kindergartens

## Slide 24: Comments on deliverables

## Slide 25: Conclusions / Actions
(All)