**Time line ”Safe pregnancy” from 15th September to recruitment starts 1th December:**

**1 dec**

**5 oct**

**20 nov**

**1 nov**

**15 sept**

1: Collect info from the Community Health Centres (CHC) - ***Eva, Jeanette, Sezer, Lena***

2: **5th** Prepare final Q1\*, ID decision, decide number of tablets, Sim vs WLAN. - ***Mirjam, Eva, Jeanette, Lena***

3: By Tablets, headphones and equipment decided on - ***Josef***

4: Finalize Q1 for use at the tablet with video and randomization allocation – ***Josef, Serhat***

5: Rigging of equipment at CHC - ***Josef***

6: Troubleshooting and testing of the equipment – ***Josef***

6: Recruitment starts

7: Making and finalize Q2 before 31. December 2017 (task will be divided later)

\*will be sent out on a hearing round, small adjustment may happen. Will be finalized approximately 16th of October.